## Registration
Section | Details
Project Name | Tricentis website
Module Name | Registration
Release Version | v1.2.3
s | Agile(sprint1)
Prepared By | Danish Jamadar
Date
1. Test Summary
Metric | Count
Total Test Cases | 20
Executed Test Cases | 20
Passed Test Cases | 9
Failed Test Cases | 11
Blocked Test Cases | NA
Not Executed Test Cases | 0
Automation Covered | yes
Manual Test Cases | 20
2. Test Case Status Distribution
Status | Count | Percentage
Passed | 9 | 45%
Failed | 11 | 55%
Blocked | 0 | 0%
Not Executed | 0 | 0%
3. Defect Summary
Metric | Count
Total Defects Logged | 0
Critical Defects | 0
High Severity Defects | 0
Medium Severity Defects | 0
Low Severity Defects | 0
Defects Fixed | 0
Defects Retested & Closed | 0
4. Test Coverage
✅ Requirements Coverage: 3 out of 3 covered.
✅ Code Coverage (if available):0%
✅ Business Scenario Coverage: 100%
5. Observations
Expected result = Should Accepts Correct format in fields
Actual result = Apart From Email Format it accepts all formats like space,number in name field
6. Risks & Issues
Risk/Issue Description | Impact | Status | Comments
Actual result = Apart From Email Format it accepts all formats like space,number in name field | Medium | pending
7. Recommendations

## login
Section | Details
Project Name | Tricentis website
Module Name | Login
Release Version | v1.2.3
s | Agile(sprint1)
Prepared By | Danish Jamadar
Date
1. Test Summary
Metric | Count
Total Test Cases | 10
Executed Test Cases | 10
Passed Test Cases | 10
Failed Test Cases | 0
Blocked Test Cases | NA
Not Executed Test Cases | 0
Automation Covered | yes
Manual Test Cases | 10
2. Test Case Status Distribution
Status | Count | Percentage
Passed | 10 | 100%
Failed | 0 | 0%
Blocked | 0 | 0%
Not Executed | 0 | 0%
3. Defect Summary
Metric | Count
Total Defects Logged | 0
Critical Defects | 0
High Severity Defects | 0
Medium Severity Defects | 0
Low Severity Defects | 0
Defects Fixed | 0
Defects Retested & Closed | 0
4. Test Coverage
✅ Requirements Coverage: 10 out of 10 covered.
✅ Code Coverage (if available):0%
✅ Business Scenario Coverage: 100%
5. Observations
NA
6. Risks & Issues
Risk/Issue Description | Impact | Status | Comments
7. Recommendations
NA

## Customer_Info
Section | Details
Project Name | Tricentis website
Module Name | Customer_Info
Release Version | v1.2.3
s | Agile(sprint1)
Prepared By | Danish Jamadar
Date
1. Test Summary
Metric | Count
Total Test Cases | 5
Executed Test Cases | 5
Passed Test Cases | 3
Failed Test Cases | 2
Blocked Test Cases | NA
Not Executed Test Cases | 0
Automation Covered | yes
Manual Test Cases | 4
2. Test Case Status Distribution
Status | Count | Percentage
Passed | 3 | 60%
Failed | 2 | 40%
Blocked | 0 | 0%
Not Executed | 0 | 0%
3. Defect Summary
Metric | Count
Total Defects Logged | 2
Critical Defects | 0
High Severity Defects | 0
Medium Severity Defects | 2
Low Severity Defects | 0
Defects Fixed | 0
Defects Retested & Closed | 0
4. Test Coverage
✅ Requirements Coverage: 5 out of 5covered.
✅ Code Coverage (if available):0%
✅ Business Scenario Coverage: 100%
5. Observations
Expected Output = if data is numeric data in first name and last name Display Error: "Enter Valid First Name"
Actual Output = Accepts Numeric Data
6. Risks & Issues
Risk/Issue Description | Impact | Status | Comments
Expected Output = if data is numeric data in first name and last name Display Error: "Enter Valid First Name"Actual Output = Accepts Numeric Data | Medium | pending
7. Recommendations
Expected Output = if data is numeric data in first name and last name Display Error: "Enter Valid First Name"

## Address
Section | Details
Project Name | Tricentis website
Module Name | Address
Release Version | v1.2.3
s | Agile(sprint1)
Prepared By | Danish Jamadar
Date
1. Test Summary
Metric | Count
Total Test Cases | 7
Executed Test Cases | 7
Passed Test Cases | 7
Failed Test Cases | 0
Blocked Test Cases | NA
Not Executed Test Cases | 0
Automation Covered | yes
Manual Test Cases | 7
2. Test Case Status Distribution
Status | Count | Percentage
Passed | 7 | 100%
Failed | 0 | 0%
Blocked | 0 | 0%
Not Executed | 0 | 0%
3. Defect Summary
Metric | Count
Total Defects Logged | 0
Critical Defects | 0
High Severity Defects | 0
Medium Severity Defects | 0
Low Severity Defects | 0
Defects Fixed | 0
Defects Retested & Closed | 0
4. Test Coverage
✅ Requirements Coverage: 7 out of 7 covered.
✅ Code Coverage (if available):0%
✅ Business Scenario Coverage: 100%
5. Observations
NA
6. Risks & Issues
Risk/Issue Description | Impact | Status | Comments
7. Recommendations
NA

## search
Section | Details
Project Name | Tricentis website
Module Name | Search
Release Version | v1.2.3
s | Agile(sprint1)
Prepared By | Danish Jamadar
Date
1. Test Summary
Metric | Count
Total Test Cases | 5
Executed Test Cases | 5
Passed Test Cases | 5
Failed Test Cases | 0
Blocked Test Cases | NA
Not Executed Test Cases | 0
Automation Covered | yes
Manual Test Cases | 5
2. Test Case Status Distribution
Status | Count | Percentage
Passed | 5 | 100%
Failed | 0 | 0%
Blocked | 0 | 0%
Not Executed | 0 | 0%
3. Defect Summary
Metric | Count
Total Defects Logged | 1
Critical Defects | 0
High Severity Defects | 0
Medium Severity Defects | 1
Low Severity Defects | 0
Defects Fixed | 0
Defects Retested & Closed | 0
4. Test Coverage
✅ Requirements Coverage: 4 out of 4 covered.
✅ Code Coverage (if available):0%
✅ Business Scenario Coverage: 100%
5. Observations
Search engine dosen't suggest relevant searches
6. Risks & Issues
Risk/Issue Description | Impact | Status | Comments
Search engine dosen't suggest relevant searches | Medium | pending
7. Recommendations

## ShopByCategory
Section | Details
Project Name | Tricentis website
Module Name | ShopByCategory
Release Version | v1.2.3
s | Agile(sprint1)
Prepared By | Danish Jamadar
Date
1. Test Summary
Metric | Count
Total Test Cases | 2
Executed Test Cases | 2
Passed Test Cases | 2
Failed Test Cases | 0
Blocked Test Cases | NA
Not Executed Test Cases | 0
Automation Covered | yes
Manual Test Cases | 2
2. Test Case Status Distribution
Status | Count | Percentage
Passed | 2 | 100%
Failed | 0 | 0%
Blocked | 0 | 0%
Not Executed | 0 | 0%
3. Defect Summary
Metric | Count
Total Defects Logged | 0
Critical Defects | 0
High Severity Defects | 0
Medium Severity Defects | 0
Low Severity Defects | 0
Defects Fixed | 0
Defects Retested & Closed | 0
4. Test Coverage
✅ Requirements Coverage: 2 out of 2 covered.
✅ Code Coverage (if available):0%
✅ Business Scenario Coverage: 100%
5. Observations
NA
6. Risks & Issues
Risk/Issue Description | Impact | Status | Comments
7. Recommendations
NA

## AddDeletetocart
Section | Details
Project Name | Tricentis website
Module Name | AddDeletetocart
Release Version | v1.2.3
s | Agile(sprint1)
Prepared By | Danish Jamadar
Date
1. Test Summary
Metric | Count
Total Test Cases | 5
Executed Test Cases | 5
Passed Test Cases | 5
Failed Test Cases | 0
Blocked Test Cases | NA
Not Executed Test Cases | 0
Automation Covered | yes
Manual Test Cases | 11
2. Test Case Status Distribution
Status | Count | Percentage
Passed | 5 | 100%
Failed | 0 | 0%
Blocked | 0 | 0%
Not Executed | 0 | 0%
3. Defect Summary
Metric | Count
Total Defects Logged | 0
Critical Defects | 0
High Severity Defects | 0
Medium Severity Defects | 0
Low Severity Defects | 0
Defects Fixed | 0
Defects Retested & Closed | 0
4. Test Coverage
✅ Requirements Coverage: 5 out of 5 covered.
✅ Code Coverage (if available):0%
✅ Business Scenario Coverage: 100%
5. Observations
6. Risks & Issues
Risk/Issue Description | Impact | Status | Comments
7. Recommendations

## CheckOut
Section | Details
Project Name | Tricentis website
Module Name | CheckOut
Release Version | v1.2.3
s | Agile(sprint1)
Prepared By | Danish Jamadar
Date
1. Test Summary
Metric | Count
Total Test Cases | 7
Executed Test Cases | 7
Passed Test Cases | 7
Failed Test Cases | 0
Blocked Test Cases | NA
Not Executed Test Cases | 0
Automation Covered | yes
Manual Test Cases | 7
2. Test Case Status Distribution
Status | Count | Percentage
Passed | 7 | 100%
Failed | 0 | 0%
Blocked | 0 | 0%
Not Executed | 0 | 0%
3. Defect Summary
Metric | Count
Total Defects Logged | 0
Critical Defects | 0
High Severity Defects | 0
Medium Severity Defects | 0
Low Severity Defects | 0
Defects Fixed | 0
Defects Retested & Closed | 0
4. Test Coverage
✅ Requirements Coverage: 7 out of 7 covered.
✅ Code Coverage (if available):0%
✅ Business Scenario Coverage: 100%
5. Observations
NA
6. Risks & Issues
Risk/Issue Description | Impact | Status | Comments
7. Recommendations
NA